## Content
M&T TOOL
| Company name | Demonstration project
| Responsible person | Vanessa Ashley
Phase I. | Introduction
Mapping of Energy Inputs
Savings potential within Area I.
Savings potential within Area II.
Deciding on feasibility of M&T introduction
Phase II. | Energy management within Area I.
Energy management within Area II.
Energy management - identifying and analysing deviations
Energy saving measures manager
Evaluation and continuation
Load User data set
The opinions expressed, the calculations performed and supporting materials provided in this software product are solely the views of the authors and should not be attributed, in any fashion, to UNEP. Although every effort has been made to ensure the accuracy of this document, the authors do not take responsibility for any inaccuracies. No use of this product may be made for resale or for any other commercial purpose whatsoever without prior permission in writing from UNEP.
Note on A7: The first phase explains the M&T methodology, leads user to self-evaluate actual level of control over energy efficiency and helps to prepare a simple business case of the M&T introduction. Your energy invoices are needed to utilise M&T tool for indication of potential for savings at your site.
Note on A12: The second phase enables user to simulate working M&T system on chosen areas and closes the loop of continuous improvement tool. Completion of the second phase is conditioned by weekly data collection and ideally by regular results analysis and improving opportunities identification.
Note on B18: Double click here to switch between your data and example data set.

## Introduction
Introduction
1. Why the M&T Tool
You can reduce your energy bill by:
- Proper selection of energy sources
- Proper energy pricing, power factor management and demand control
- Energy efficiency
This tool will help you to start with systematic exploration of energy efficiency opportunities within your site. Efficiency improvements to generate more economic output with less energy and material input is of increasing importance for SMEs. Main reasons are growing energy prices and the increased availability of more clever and cheaper techniques for energy efficiency. However, you can not manage what you can not measure. If you do not measure efficiency of energy use, how do you want to control it? This tool will show you how you to do it through M&T.
Manage your flows, manage your money
The Monitoring and Targeting Tool is targeted primarily at self-help in managing energy efficiency within SME size industrial facilities. It addresses the common problem experienced by many companies: the lack of control over the energy costs within industrial sites.
Do not accept energy consumption as a fixed cost that your enterprise has no control over. Let's start by adding value to your business by exploring opportunities for energy management in your site and by piloting its implementation through the monitoring and targeting (M&T) tool.
The M&T Tool enables to:
- Visualise energy consumption and cost trends in the past
- Estimate potential for savings within processes and buildings
- Set up performance targets for energy management programs (and to determine future energy use when planning, for example, an increase in production volume)
- Identify areas where energy is not utilised efficiently, understand causes of these losses and to develop and monitor energy conservation measures
2. How M&T works
The M&T Tool builds on the concept of Monitoring and Targeting (M&T). M&T is one of the most effective energy management tools to help reduce energy costs through improved energy efficiency and energy management control. This well established tool can bring many other benefits such as: increased resource efficiency, better environmental performance or better production budgeting.
The very basic principle of M&T is to track real efficiency of energy use by monitoring energy consumption together with its influencing factors (for example production volume or ambient temperature) and understanding their dependance through regression analysis.
Regression analysis is done automatically by the tool. This calculated dependence is within M&T called the "target". The principle of working with M&T is in identifying and analysing deviations between actual performance and the target. This leads to understanding causes of energy losses and enables development of energy conservation measures. After an energy saving measure is implemented, the deviations between actual performance and the target shows its actual performance.
Implementation of M&T tool comprises these steps:
3. How to use the M&T Tool
The M&T Tool enables users to learn and understand the basics of the M&T technique and to pilot M&T within a specific site. Industrial processes and space heating within buildings are the two basic areas offered for piloting M&T within the tool. However, any other area where energy is utilised can be selected as well. For the area selected, you will estimate the energy savings potential (PHASE I) and pilot how M&T works in practice (PHASE II).
The M&T Tool guides user interactively through the M&T in two phases:
Phase I.
Explains the M&T principle, helps the user to self-evaluate the actual level of control over energy efficiency and helps to prepare a simple business case of the M&T introduction.
Your input:
a) energy invoices from your site (for two selected areas, best for the last three years)
b) data on factors influencing energy consumption (most often production volume or temperature) for the same time periods as energy invoices
Also you will need to estimate demand for monitoring equipment within your site in order to know costs of introduction of the necessary submeters.
Output for your site:
■ visualisation of energy consumption and cost trends in the past
■ feasibility of M&T introduction within selected areas (quantification of potential for savings and costs of M&T introduction)
Internal output: Set up of performance targets (baselines) for implementation of M&T within selected areas in Phase II
Phase II.
Enables to implement M&T system within the two areas selected in Phase I.
Your input:
a) weekly data on energy consumption within the selected area
b) weekly data on factors influencing energy consumption within selected area (production volume or degree days)
Output for your site:
■ identification of areas and time periods within which energy is lost
■ understanding of causes of the identified losses
■ development of energy conservation measures
■ quantification of benefits of implemented energy conservation measures
Evaluation of performance of implemented energy efficieny measures closes the M&T loop of continuous improvement.
Instructions for using the M&T Tool
Users are allowed to edit all cells with deep yellow background. The description of expected input is available in the form of interactive notes displayed when moving the mouse over the cells with small red triangles in the top right cell corner.
You should choose one or two areas for utilisation of the tool first. The major limitation is usually the availability of data here. Therefore we propose you start by production and heating as two typical areas where energy is used. The chosen area can be also a cost centre within the facility. However, you will need a sub metering of energy consumption and of the driving factors in that case.
We recommend to go through particular screens of the tool using the downloaded data of the example (downloadable within Content) first. After understanding how the tool works you start by pushing the button "load user data set" at the content screen and continue by filling in your own data on energy consumption and costs from your energy bills (within the screen Inputs). Note: If you double-click on Load example data set, a new sheet Case Study occurs.
Note: Note that this demonstration tool is not capable to support a full scale M&T system in more complex cases. A full scale M&T system usually requires more areas (cost centres) to be managed separately. Also, not all industrial processes will have targets who approximate the "y = mx + c" form (as simplified within this tool).
4. M&T step by step
We recommend to read this theoretical description before you start to work with the M&T tool. While working with particular screens there will be a link to relevant parts of this text under this questionmark:
Phase I: Estimating potential for savings
1) Measure
You can not manage what you can not measure. However, the energy consumption data are only half of the overall story. Without something to relate energy consumption to, the manager is unable to determine whether the consumption represents good, average or poor performance. Measuring energy performance thus involves knowledge of those factors that influence it, whether these are production levels or ambient conditions. Energy consumption data need to be related to them - this is the basic principle of M&T.
Therefore any M&T effort has to start by:
Monitoring energy consumption - screen Inputs and (at the same time periods)
Monitoring factor(s) influencing energy consumption - screens Savings Area I and Savings Area II
2) Calculate
Data collected within step 1) are processed by statistical analysis within step 2):
Regression analysis calculated by the tool within Savings Area I shows the relationship between energy consumption and its influcening (driving) factor - in this case production (we plot a series of values of production against associated energy consumption in a production scatter plot).
Consumption of energy expected within the existing process can be calculated from the statistically developed relationship between production and consumption - so called "target". Relationship between consumption and production is energy efficiency - value we want to control and improve.
Correlation shows the degree of variability in the energy performance. It is driven by operational factors influencing energy efficiency.
Screen Savings Area II utilises the same regression analysis to show dependence of energy consumption for space heating on outdoor temperature expressed in degree-days (degree-days for given area can be found on the internet - this information is provided by meteorological institutions).
The energy saving potential is indicated here in a very simple way (see picture 1): all performance values which are above the target (calculated relationship between energy consumption and production) are considered to be avoidable losses. These losses represent potential for non-investment savings which could be achieved by better operation of the existing technology and/or building.
Picture 1: Estimation of energy saving potential is done in a very simple way - all performance values which are above the calculated relationship between energy consumption and production (so called target) are considered to be avoidable losses.
Estimation of this potential is related to specific facilities or energy cost centres you choose at the first screen of the calculator (Inputs). Be aware that all calculations within the whole tool (Phase I and Phase II) are related to the same areas (cost centres) chosen.
You can explore the feasibility of introducing an energy management system based on M&T in your site by comparing estimation of savings and estimation of costs of introducing M&T as shown within the screen Feasibility.
The regression analysis developed within Phase I is utilised for setting up the baseline (target) within the tool in order to simplify our pilot experience with M&T. In order to better understand the "targeting" part of M&T, there is more theoretical information provide on target setting here:
Target setting
Regression analysis shows relationship between energy consumption and its driving factor - in this case production volume (we plot a series of values of production against associated energy consumption in a production scatter plot).
Through the regression analysis we set a "target" (red line in the graph): Target in M&T is consumption of energy expected within the existing process as calculated from the statistically developed relationship between production and consumption (see Picture 2). This statistical analysis of data is done in the same way as analysis within screens Savings Area I and II and M&T Area I and II.
Picture 2: The target (red line) is the statistically developed relationship between the driving factor for energy use (in this case production volume) and energy consumption.
We can observe three main features of the investigated process within the graph:
- Intercept - the implied consumption even if no production took place, this is generally assumed to be the base load of the system
Processes may have high intercepts for various reasons:
- The process may have distinctive features that lead to high base loads, e.g. rubber curing and moulding where much of the heat input is required to maintain the temperature of the moulding machine
- There is a fault in the process which is leading to a high base load, e.g. faults in steam traps, compressed air leaks, etc.
-The intercept represents the capacity of the machine. The variations in production are due to the machine working at full capacity but with different duties. Here an example could be burner gas consumption for a hot air drier, the drying capacity of the machine will depend on the input moisture rate of the material to be dried.
- Scatter - the degree of variability in the energy performance, this tends to be driven by operational factors. This is the correlation which shows the degree of variability in the energy performance.
Scatter may also have multiple causes:
- The production is not the only significant influencing factor for energy consumption. In an externally located process heater for example, ambient conditions may also need to be considered. Although it is impossible to show these forms of relationships graphically, it is possible to undertake multiple regression analyses to determine the relationship between energy consumption and multiple variables. For multiple regression techniques to work, it is important to have a significant number of data points on which to undertake the analysis. The techniques tend to be unreliable with small datasets, equally multiple regression should be limited to three variables.
- There is a general lack of control, this is most likely where the actions of the process operator have a significant impact on energy consumption
- There is no relation between production and consumption, typically this would be true for mechanical processes, such as conveying, cutting, size reduction, etc. Here the relation tends to be between energy and the 'production hours' of the machinery concerned hence different forms of graphs can be generated and used to develop targets.
- Slope - the direct relationship between production and consumption, the efficiency of the process can be assessed from the slope.
The equation of the best fit line as shown within Picture 2 represents average historical performance and can be used as the initial target for the process, with the operational objective being to ensure that all future points on the production scatter graph fall on or beneath the target line. This is evidently an achievable target since it is based on historical performance, it is also a challenging target since it implies better than average historical performance.
Specifics of space heating
Energy management within buildings has to consider as major influencing factor usually the outside temperature (measured in degree-days). However, similar to technology, there can be also other factors influencing energy consumption within buildings as utilisation of the space and resulting change of desired inside temperature. This simple M&T tool can be utilised only for analysis of a single influencing factor.
Note: The target (expected performance) has to be calculated within step 2) Calculate first. This means that step 1) Measure and 2) Calculate go back and forth within the M&T implementation before the target (baseline) is set up. M&T implementation can progress to step 3) Compare (identification of deviations between the expected and actual performance) only later when the target is available for calculation of the expected energy consumption. In order to integrate this feature of M&T into the tool, the target is calculated from the historical data first (as an output of the Phase I) in order to enable easy piloting of M&T (within the Phase II).
Phase II: Piloting energy management system
To start with energy management you will need more detailed (weekly) data from the selected areas to be filled in to screens M&T Area I and M&T Area II.
3) Compare
Having the target you can start by practicing energy management at the given area by identifying and analysing Deviations between actual performance and the target.
M&T software enables to evaluate implemented energy conservation measures and to calculate cumulative savings for the whole cost centre. Again, this is done by identifying and analysing deviations between actual performance and the target.
4) Communicate
Each deviation can lead to understanding causes of inefficiencies. However, it has to be communicated to those who influcence the energy efficiency and who understand the process. The screen Manager will help you to implement this crucial step.
5) Take action
Understanding the causes of deviations leads to development of energy conservation measures. The Manager can assist you also within this important activity.
Performance of each implemented measure can be easily evaluated through implementation of steps 1) - 3): You 1) measure new data on driving factor and energy consumption, 2) calculate expected consumption and 3) compare it with the target. If there are savings due to the implemented energy conservation measures, they will be visualised as a variance from target within the screen Deviations and as net saving or losses within the screen Continuation.
5. Continuing by full scale M&T implementation
If your experience with piloting the M&T tool within your site is positive, you should consider to continue. Only SMEs with a simple structure of energy use (two cost centres) can use the M&T tool here. Most probably, you will need more sophisticated software support to do this. The key success factors of full scale M&T implementation are largely determined by organisational capabilities:
- Senior Management Commitment: Without the commitment of the senior management M&T will rarely succeed. This commitment must take a number of forms: Initially the management must approve the budget required to install the meters, subsequently they must convey to their managers the importance of energy management and follow this through with frequent reviews of performance. Finally they must ensure that budgets are genuinely devolved and equally that budgets are set aside for implementing energy saving measures.
- Accountability / devolved budgeting. Without the production managers being held accountable for energy performance they will focus their attention on those aspects of production against which their own personal performance is measured.
- Empowerment. Another aspect of accountability must be that the production managers and production departments are empowered to make changes to improve their energy performance.
- Positive reinforcement: The M&T system has to have sufficient granularity / resolution such that changes made by individuals are evident in the overall performance improvement. If people can see that what they do makes a difference they are more likely to maintain good performance.
- Culture Fit: Organisations that already have management systems in place are more likely to succeed with M&T since they can embed this systemised approach to energy management within their existing systems.
Energy Consumption
Production Volume
Energy Consumption
Production Volume
?

## Inputs
Mapping of Energy Inputs
... is the first step for better management of energy and money flows within TECHNOLOGY (Process) and BUILDINGS (Space heating).
In order to estimate the potential for savings start by mapping your energy inputs as recorded in your energy bills from last 3 years:
Monthly periods | Process |  | Space heating & DHW |  | Currency | €
| Consumption | Cost | Consumption | Cost | Ex. Rate | 0.637 | € / $ | Unit price
| kWh | € | Nm3 | € |  |  |  | Process
2004/1 | 3233750.5 | 167302.328 | 66916.5 | 13392.96 |  |  |  | 0.051736 | 0.20014
2004/2 | 3042366.1 | 160745.452 | 64431.2 | 12937.3176 |  |  |  | 0.052836 | 0.20079
2004/3 | 3545457.5 | 185257.08 | 58780.4 | 11840.4684 |  |  |  | 0.052252 | 0.20144
2004/4 | 3570384.6 | 154153.232 | 47184.3 | 10493.258 |  |  |  | 0.043176 | 0.22239
2004/5 | 3666713.2 | 152152.348 | 32985.1 | 7465.1892 |  |  |  | 0.041496 | 0.22632
2004/6 | 3148137.5 | 144028.492 | 15715.3 | 3782.2928 |  |  |  | 0.04575 | 0.24068
2004/7 | 3404426.1 | 149223.684 | 17690.2 | 4203.4508 |  |  |  | 0.043832 | 0.23761
2004/8 | 3472146.8 | 152211.192 | 12075.2 | 3006.018 |  |  |  | 0.043838 | 0.24894
2004/9 | 3197067.2 | 149954.064 | 24191.7 | 5589.9392 |  |  |  | 0.046904 | 0.23107
2004/10 | 3259460.2 | 166672.904 | 32882.9 | 7181.48 |  |  |  | 0.051135 | 0.2184
2004/11 | 3640018.8 | 183129.672 | 54075.4 | 11532.1612 |  |  |  | 0.05031 | 0.21326
2004/12 | 3662697 | 184365.772 | 61991.3 | 13220.316 |  |  |  | 0.050336 | 0.21326
2005/1 | 3665758.6 | 200952.824 | 68426.3 | 14447.176 |  |  |  | 0.054819 | 0.21113
2005/2 | 3683109.1 | 201835.672 | 49009.4 | 10546.56 |  |  |  | 0.0548 | 0.21519
2005/3 | 4269242.1 | 235967.072 | 49632.6 | 10671.76 |  |  |  | 0.055271 | 0.21502
2005/4 | 4064433.1 | 223152.24 | 36089 | 7637.632 |  |  |  | 0.054904 | 0.21163
2005/5 | 3784107.5 | 213794.352 | 29954.3 | 6457.84 |  |  |  | 0.056498 | 0.21559
2005/6 | 3906042.6 | 225753.972 | 20588 | 4657.848 |  |  |  | 0.057796 | 0.22624
2005/7 | 4078967.1 | 238720.332 | 19724.4 | 4491.904 |  |  |  | 0.058525 | 0.22773
2005/8 | 4245918.9 | 234295.376 | 11204.6 | 2854.56 |  |  |  | 0.055181 | 0.25477
2005/9 | 3978876 | 218849.484 | 47330.3 | 9797.16 |  |  |  | 0.055003 | 0.207
2005/10 | 4094073 | 223582.572 | 37512.5 | 8953.532 |  |  |  | 0.054611 | 0.23868
2005/11 | 4260130.4 | 231958.536 | 49596.9 | 11611.94 |  |  |  | 0.054449 | 0.23413
2005/12 | 4184127.9 | 228603.864 | 63263.4 | 14618.396 |  |  |  | 0.054636 | 0.23107
2006/1 | 3771852.5 | 231557.156 | 60022.5833 | 16029.84 |  |  |  | 0.061391 | 0.26706
2006/2 | 3645806.6 | 226481.344 | 63769.975 | 17096.76 |  |  |  | 0.062121 | 0.2681
2006/3 | 4017984.5 | 249177.456 | 55087.225 | 14857.56 |  |  |  | 0.062016 | 0.26971
2006/4 | 3370254 | 209845.788 | 32842.1708 | 8972.04 |  |  |  | 0.062264 | 0.27319
2006/5 | 3398793.1 | 213764.648 | 26232.6875 | 7324.56 |  |  |  | 0.062894 | 0.27922
2006/6 | 3382749.8 | 214831.36 | 19405.6625 | 5631.48 |  |  |  | 0.063508 | 0.2902
2006/7 | 3372468.5 | 209288.744 | 16896.3667 | 5241.76 |  |  |  | 0.062058 | 0.31023
2006/8 | 3568355 | 226725.744 | 16741.25 | 5194.64 |  |  |  | 0.063538 | 0.31029
2006/9 | 3572599.1 | 224612.812 | 18777.6292 | 5724.08 |  |  |  | 0.062871 | 0.30484
2006/10 | 3648240.4 | 223257.708 | 29735.1083 | 10270.08
2006/11 | 3947412.9 | 241412.68 | 47146.0083 | 15814.92
2006/12 | 3742011 | 229015.584 | 50999 | 17047.28
You have visualised patterns hidden in your historical energy bills.
Let's explore what are the driving forces behind these flows!
?
Note on B6: Insert monthly periods for particular batches based on available invoicing data.
Note on C6: Insert name of specific energy cost centre
Note on E6: Insert name of specific energy cost centre
Note on H6: Fill in currency of your energy invoices
Note on C7: Fill in energy consumption of the specific account centre in chosen time period
Note on D7: Fill in total price paid for consumption of energy in chosen time periods.
Note on E7: Fill in energy consumption of the specific account centre in chosen time periods
Note on F7: Fill in total price paid for consumption of energy within chosen time periods.
Note on H7: Fill in exchange rate of selected currency and USD
Note on C8: Fill in physical units
Note on E8: Fill in physical units

## Savings Area I
Savings potential within Area I.
The most common driving factor for energy use in process is volume of production
Continue by filling in your production data in the same time periods as the energy inputs.
Monthly periods | Process
| Consumption | Production | Target cons. | Saving potential
| kWh | t | kWh | kWh | 119.0208 | 731655.1505
2004/1 | 3233750.5 | 20720 | 3197766.9621 | 0 | 14.7582 | 367140.8514
2004/2 | 3042366.1 | 20368 | 3155871.6263 | 113505.5263 | 0.6567 | 198952.8965
2004/3 | 3545457.5 | 22648 | 3427239.1423 | 0 | 65.0397 | 34
2004/4 | 3570384.6 | 22187 | 3372370.5349 | 0
2004/5 | 3666713.2 | 22913 | 3458779.665 | 0
2004/6 | 3148137.5 | 18789 | 2967937.7195 | 0
2004/7 | 3404426.1 | 23618 | 3542689.3574 | 138263.2574
2004/8 | 3472146.8 | 25714 | 3792157.0387 | 320010.2387
2004/9 | 3197067.2 | 22211 | 3375227.0351 | 178159.8351
2004/10 | 3259460.2 | 22965 | 3464968.7487 | 205508.5487
2004/11 | 3640018.8 | 24859 | 3690394.2203 | 50375.4203 | Consumption = 731655 + Production * 119.0208
2004/12 | 3662697 | 22466 | 3405577.3494 | 0
2005/1 | 3665758.6 | 24809 | 3684443.1782 | 18684.5782 | Correlation = 0.66
2005/2 | 3683109.1 | 25027 | 3710389.7214 | 27280.6214
2005/3 | 4269242.1 | 27840 | 4045195.3453 | 0 | Saving potential = 993770 kWh/year
2005/4 | 4064433.1 | 27630 | 4020200.9688 | 0
2005/5 | 3784107.5 | 26330 | 3865473.8764 | 81366.3764
2005/6 | 3906042.6 | 25424 | 3757640.995 | 0
2005/7 | 4078967.1 | 25964 | 3821912.2488 | 0
2005/8 | 4245918.9 | 27050 | 3951168.8814 | 0
2005/9 | 3978876 | 27020 | 3947598.2562 | 0
2005/10 | 4094073 | 26655 | 3904155.6495 | 0
2005/11 | 4260130.4 | 27190 | 3967831.7991 | 0
2005/12 | 4184127.9 | 26000 | 3826196.9991 | 0
2006/1 | 3771852.5 | 27422 | 3995444.634 | 223592.134
2006/2 | 3645806.6 | 25074 | 3715983.7009 | 70177.1009
2006/3 | 4017984.5 | 28316 | 4101849.2653 | 83864.7653
2006/4 | 3370254 | 24820 | 3685752.4075 | 315498.4075
2006/5 | 3398793.1 | 23880 | 3573872.8176 | 175079.7176
2006/6 | 3382749.8 | 24170 | 3608388.8613 | 225639.0613
2006/7 | 3372468.5 | 24960 | 3702415.3251 | 329946.8251
2006/8 | 3568355 | 24750 | 3677420.9487 | 109065.9487
2006/9 | 3572599.1 | 22660 | 3428667.3924 | 0
2006/10 | 3648240.4 | 26655 | 3904155.6495 | 255915.2495
2006/11 | 3947412.9 | 27050 | 3951168.8814 | 3755.9814
2006/12 | 3742011 | 25760 | 3797631.9974 | 55620.9974
You have visualised dependence of energy consumption on its driving factor:
Regression analysis shows efficiency of your process and indicated potential for savings from non investment measures.
?
Note on B6: Insert monthly periods for particular batches based on available invoicing data.
Note on C6: Energy account centre name
Note on C7: Energy consumption of the specific energy account centre
Note on D7: Insert the name of selected influencing factor - variable
Note on E7: The theoretical consumption level calculated using the target equation and variable value in given time period
Note on F7: Simplified savings potential evaluation. The points above the red best fit line are assumed to reflect periods with higher than necessary consumption and the difference between the point and line is treated as achievable saving.
Note on D8: Insert physical units of selected influencing factor

## Savings Area II
Savings potential within Area II.
Driving factor for space heating energy consumption within your buildings is outside temperature measured by degree-days.
Continue by filling in degree-days which can be found on the internet within local meteorological data.
Monthly periods | Space heating & DHW
| Consumption | Degree days | Target cons. | Saving potential
| Nm3 | DST | Nm3 | Nm3 | 75.2353 | 10369.0387
2004/1 | 66916.5 | 712.6 | 63981.7158 | 0 | 4.398 | 1954.5071
2004/2 | 64431.2 | 693.8 | 62567.2921 | 0 | 0.89591 | 5976.5188
2004/3 | 58780.4 | 519.6 | 49461.3023 | 0 | 292.6385 | 34
2004/4 | 47184.3 | 405.2 | 40854.3836 | 0
2004/5 | 32985.1 | 185.4 | 24317.664 | 0
2004/6 | 15715.3 | 54.4 | 14461.8392 | 0
2004/7 | 17690.2 | 84.8 | 16748.9925 | 0
2004/8 | 12075.2 | 50.2 | 14145.851 | 2070.651
2004/9 | 24191.7 | 220.8 | 26980.9937 | 2789.2937
2004/10 | 32882.9 | 495.3 | 47633.0844 | 14750.1844
2004/11 | 54075.4 | 512.5 | 48927.1316 | 0 | Consumption = 10369 + Degree days * 75.2353
2004/12 | 61991.3 | 662.2 | 60189.8565 | 0
2005/1 | 68426.3 | 751.2 | 66885.7985 | 0 | Correlation = 0.9
2005/2 | 49009.4 | 558.5 | 52387.9556 | 3378.5556
2005/3 | 49632.6 | 545.4 | 51402.3731 | 1769.7731 | Saving potential = 23519 Nm3/year
2005/4 | 36089 | 349.1 | 36633.6831 | 544.6831
2005/5 | 29954.3 | 279.2 | 31374.7354 | 1420.4354
2005/6 | 20588 | 150.3 | 21676.9048 | 1088.9048
2005/7 | 19724.4 | 98.9 | 17809.8102 | 0
2005/8 | 11204.6 | 76.9 | 16154.6336 | 4950.0336
2005/9 | 47330.3 | 213.1 | 26401.6819 | 0
2005/10 | 37512.5 | 360.9 | 37521.4597 | 8.9597
2005/11 | 49596.9 | 527.1 | 50025.5671 | 428.6671
2005/12 | 63263.4 | 665.8 | 60460.7036 | 0
2006/1 | 60022.5833 | 635.2 | 58158.5033 | 0
2006/2 | 63769.975 | 677.4 | 61333.4331 | 0
2006/3 | 55087.225 | 583.6 | 54276.3617 | 0
2006/4 | 32842.1708 | 337.3 | 35745.9065 | 2903.7357
2006/5 | 26232.6875 | 231.6 | 27793.535 | 1560.8475
2006/6 | 19405.6625 | 121.8 | 19532.6987 | 127.0362
2006/7 | 16896.3667 | 97.9 | 17734.5749 | 838.2083
2006/8 | 16741.25 | 139.9 | 20894.4577 | 4153.2077
2006/9 | 18777.6292 | 186.1 | 24370.3287 | 5592.6995
2006/10 | 29735.1083 | 348.9 | 36618.636 | 6883.5277
2006/11 | 47146.0083 | 561.9 | 52643.7556 | 5497.7473
2006/12 | 50999 | 670.3 | 60799.2625 | 9800.2625
You have visualised dependence on energy consumption on its driving factor (outside temperature measured by degree-days).
Regression analysis indicates efficiency of your heating and enables estimation of potential for non investment savings.
?
Note on B6: Insert monthly periods for particular batches based on available invoicing data.
Note on C6: Energy account centre name
Note on C7: Energy consumption of the specific energy account centre
Note on D7: Insert the name of selected influencing factor - variable
Note on E7: The theoretical consumption level calculated using the target equation and variable value in given time period
Note on F7: Simplified savings potential evaluation. The points above the red best fit line are assumed to reflect periods with higher than necessary consumption and the difference between the point and line is treated as achievable saving.
Note on D8: Insert physical units of selected influencing factor

## Feasibility
Deciding on feasibility of M&T introduction
Let's explore the feasibility of introducing an energy management system based on M&T in your site:
Having rough estimation of potential for savings estimate the costs of introducing M&T here:
Project budget
Meter type | Cost | Number of meters | Cost
Electricity - 3-phase meter incl. CTs | 599.5294 | 15 | 8992.9412
Cold water - DN50 turbine | 374.7059 | 3 | 1124.1176
Natural gas - DN100 | 1873.5294 | 5 | 9367.6471
Cold water - DN200 turbine | 936.7647 | 2 | 1873.5294
Steam - DN50 orifice plate | 4121.7647 | 4 | 16487.0588
Cold water - DN100 turbine | 562.0588 | 4 | 2248.2353
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
| 0 |  | 0
Total meters |  | 33 | 40093.5294
Data acquisition system |  |  | 10000
M&T software |  |  | 12000
Technical assistance |  |  | 18000
Total M&T Introduction cost |  |  | 80093.5294
Project parameters
Saving potential - Process |  | 61768.9157 | €/year
Saving potential - Space heating & DHW |  | 6943.3357 | €/year
Total saving potential |  | 68712.2514 | €/year
M&T introduction pay-back period |  | 1.1656 | year(s)
Discount rate |  | 10 | %
Project NPV (1 year implementation + 10 years run) |  | 282618.7896 | €
Project IRR |  | 67.9544 | %
Does the indicative project performance make sense from your business perspective?
Let's start introduction of M&T by piloting its basic steps as described within the next screens.
Utility - Meter Type | Average Cost $ |  | Avg. Cost |  |  |  |  | Discounted C.F.
Electricity - 1-phase meter | 235.2941 | 4000 | 6279.4349 | 0 | 1 | -80093.5294 | -80093.5294 | -80093.5294
Electricity - 3-phase meter | 352.9412 | 6000 | 9419.1523 | 1 | 0.90909 | 34356.1257 | 31232.8415 | -48860.6879
Electricity - 1-phase meter incl. CT | 411.7647 | 7000 | 10989.011 | 2 | 0.82645 | 68712.2514 | 56786.9846 | 7926.2967
Electricity - 3-phase meter incl. CTs | 941.1765 | 16000 | 25117.7394 | 3 | 0.75131 | 68712.2514 | 51624.5315 | 59550.8282
Cold water - DN25 turbine | 235.2941 | 4000 | 6279.4349 | 4 | 0.68301 | 68712.2514 | 46931.3922 | 106482.2204
Cold water - DN50 turbine | 588.2353 | 10000 | 15698.5871 | 5 | 0.62092 | 68712.2514 | 42664.902 | 149147.1224
Cold water - DN100 turbine | 882.3529 | 15000 | 23547.8807 | 6 | 0.56447 | 68712.2514 | 38786.2746 | 187933.397
Cold water - DN200 turbine | 1470.5882 | 25000 | 39246.4678 | 7 | 0.51316 | 68712.2514 | 35260.2496 | 223193.6466
Hot water - DN25 turbine | 294.1176 | 5000 | 7849.2936 | 8 | 0.46651 | 68712.2514 | 32054.7724 | 255248.419
Hot water - DN50 turbine | 705.8824 | 12000 | 18838.3046 | 9 | 0.4241 | 68712.2514 | 29140.7022 | 284389.1211
Hot water - DN100 turbine | 1294.1176 | 22000 | 34536.8917 | 10 | 0.38554 | 68712.2514 | 26491.5474 | 310880.6685
Hot water - DN200 turbine | 2058.8235 | 35000 | 54945.0549
Steam - DN25 orifice plate | 3529.4118 | 60000 | 94191.5228
Steam - DN50 orifice plate | 6470.5882 | 110000 | 172684.4584
Steam - DN100 orifice plate | 9411.7647 | 160000 | 251177.394
Steam - DN200 orifice plate | 14705.8824 | 250000 | 392464.6782
Natural gas - DN25 | 882.3529 | 15000 | 23547.8807
Natural gas - DN50 | 2058.8235 | 35000 | 54945.0549
Natural gas - DN100 | 2941.1765 | 50000 | 78492.9356
Natural gas - DN200 | 5294.1176 | 90000 | 141287.2841
?
Note on B7: From the list select the utility and type of needed metering equipment
Note on D7: Insert number of selected metering equipment
Note on E24: Insert estimated cost of data acquisition system introduction/improvement
Note on E25: Insert the estimated cost for M&T software licence and setup
Note on E26: Insert the estimated cost of external technical assistance. It usually includes systém facilitation, saving opportunities identification, staff training etc.
Note on B34: Insert the discount rate representing your value of money

## M&T Area I
Energy management within Area I.
You will implement energy management within Area I (energy consuming unit chosen within screen Inputs).
Monitor production and related energy consumption within this area weekly.
Enter the data into a new more detailed regression analysis tool here:
Weekly periods | Process
| Consumption | Production | SER | Target cons. | Variance | Cumulated savings
| kWh | t | kWh/t | kWh | kWh | € | 168843.4963 | 119.0208
2007-01-01 | 727095.7484 | 3791 | 191.7952 | 620051.502 | -107044.2464 | -6653.4568
2007-01-08 | 802061.6968 | 7501 | 106.9273 | 1061618.8196 | 259557.1228 | 9479.6111 | 3548 | 591129.4378
2007-01-15 | 904960.5104 | 7530 | 120.1807 | 1065070.424 | 160109.9136 | 19431.4247 | 10833 | 1458196.2596
2007-01-22 | 858397.1694 | 6792 | 126.3836 | 977233.0438 | 118835.8743 | 26817.8035
2007-01-29 | 879516.0009 | 5366 | 163.9053 | 807509.3255 | -72006.6754 | 22342.1468
2007-02-05 | 1012356.2353 | 6161 | 164.3169 | 902130.8935 | -110225.3417 | 15490.9654
2007-02-12 | 519569.4084 | 4032 | 128.8615 | 648735.5245 | 129166.1161 | 23519.4321
2007-02-19 | 829805.8918 | 5094 | 162.8987 | 775135.6569 | -54670.2349 | 20121.3416
2007-02-26 | 1034878.3396 | 8793 | 117.6934 | 1215393.7453 | 180515.4057 | 31341.4817
2007-03-05 | 1378681.3276 | 8900 | 154.908 | 1228128.9752 | -150552.3524 | 21983.7292
2007-03-12 | 1190863.4919 | 7481 | 159.1851 | 1059238.4028 | -131625.0891 | 13802.4222
2007-03-19 | 1029624.249 | 7150 | 144.0034 | 1019842.5046 | -9781.7443 | 13194.4268
2007-03-26 | 759197.9229 | 3548 | 213.9791 | 591129.4378 | -168068.4851 | 2747.9391
2007-04-02 | 1026099.0322 | 5534 | 185.4172 | 827504.8267 | -198594.2055 | -9595.9093
2007-04-09 | 1401709.9041 | 9966 | 140.6492 | 1355005.191 | -46704.7131 | -12498.8938
2007-04-16 | 834500.9114 | 7083 | 117.8174 | 1011868.1083 | 177367.1969 | -1474.4342
2007-04-23 | 1312973.4332 | 8239 | 159.3608 | 1149456.1997 | -163517.2334 | -11638.0336
2007-04-30 | 981440.4992 | 9203 | 106.6435 | 1264192.2898 | 282751.7906 | 5936.7252
2007-05-07 | 1290224.3978 | 8481 | 152.1312 | 1178259.2431 | -111965.1546 | -1022.5962
2007-05-14 | 652093.3349 | 3561 | 183.1208 | 592676.7087 | -59416.6262 | -4715.7041
2007-05-21 | 862924.2768 | 5377 | 160.4843 | 808818.5547 | -54105.7221 | -8078.7068
2007-05-28 | 831574.5798 | 4714 | 176.4053 | 729907.7376 | -101666.8422 | -14397.9249
2007-06-04 | 1020255.2829 | 7924 | 128.7551 | 1111964.635 | 91709.3522 | -8697.6259
2007-06-11 | 715407.4956 | 5944 | 120.3579 | 876303.3712 | 160895.8756 | 1303.0401
2007-06-18 | 939207.7661 | 7832 | 119.9193 | 1101014.7177 | 161806.9516 | 11360.335
2007-06-25 | 756369.0658 | 6820 | 110.9046 | 980565.6273 | 224196.5615 | 25295.527
2007-07-02 | 837592.7642 | 5601 | 149.5434 | 835479.223 | -2113.5412 | 25164.1574
2007-07-09 | 1078530.6381 | 8467 | 127.3805 | 1176592.9513 | 98062.3132 | 31259.3319
2007-07-16 | 901782.5673 | 4449 | 202.6933 | 698367.2149 | -203415.3524 | 18615.8196
2007-07-23 | 1304427.4327 | 9015 | 144.6952 | 1241816.3718 | -62611.0608 | 14724.158
2007-07-30 | 657090.6458 | 3841 | 171.0728 | 626002.544 | -31088.1018 | 12791.8417
2007-08-06 | 1611044.5221 | 10502 | 153.4036 | 1418800.3614 | -192244.1606 | 842.6875
2007-08-13 | 1034132.514 | 7830 | 132.0731 | 1100776.6761 | 66644.1621 | 4985.0311
2007-08-20 | 1298037.9521 | 8036 | 161.5279 | 1125294.9692 | -172742.9829 | -5752.0053
2007-08-27 | 1024971.3288 | 7373 | 139.0169 | 1046384.152 | 21412.8232 | -4421.067
2007-09-03 | 741465.0635 | 4716 | 157.2233 | 730145.7793 | -11319.2843 | -5124.6299
2007-09-10 | 962318.1811 | 7048 | 136.5378 | 1007702.3789 | 45384.1978 | -2303.7235
2007-09-17 | 1124145.7584 | 7578 | 148.3433 | 1070783.4243 | -53362.3341 | -5620.5201
2007-09-24 | 861832.967 | 7302 | 118.027 | 1037933.6724 | 176100.7053 | 5325.2194
2007-10-01 | 718706.8673 | 4705 | 152.7539 | 728836.55 | 10129.6827 | 5954.8413
2007-10-08 | 1594406.6305 | 9645 | 165.3091 | 1316799.5013 | -277607.1292 | -11300.1452
2007-10-15 | 1620255.7079 | 10762 | 150.5534 | 1449745.7799 | -170509.928 | -21898.3835
2007-10-22 | 1228239.2614 | 10707 | 114.7137 | 1443199.6337 | 214960.3723 | -8537.2774
2007-10-29 | 932333.0531 | 9731 | 95.8106 | 1327035.2935 | 394702.2405 | 15995.8889
2007-11-05 | 813124.1722 | 4113 | 197.6961 | 658376.2125 | -154747.9597 | 6377.3536
2007-11-12 | 450930.896 | 3734 | 120.7635 | 613267.3141 | 162336.4181 | 16467.5581
2007-11-19 | 527917.4643 | 4103 | 128.6662 | 657186.0041 | 129268.5398 | 24502.3911
2007-11-26 | 1713113.5489 | 10833 | 158.1384 | 1458196.2596 | -254917.2894 | 8657.7173
2007-12-03 | 1171003.0154 | 9406 | 124.4953 | 1288353.5204 | 117350.505 | 15951.7713
2007-12-10 | 939682.3762 | 5604 | 167.6807 | 835836.2855 | -103846.0907 | 9497.0995
2007-12-17 | 1048882.8211 | 6084 | 172.4002 | 892966.2888 | -155916.5322 | -194.0697
2007-12-24 | 775665.078 | 4935 | 157.1763 | 756211.3433 | -19453.7347 | -1403.2387
2007-12-31 | 1121265.6086 | 9249 | 121.231 | 1269667.2485 | 148401.6399 | 7820.8339
See results within screen "Deviations"
?
Note on B7: Insert labels of weekly time periods
Note on C7: Energy account centre name
Note on C8: Insert corresponding energy account centre consumption
Note on D8: Insert corresponding value of particular influencing factor - variable
Note on E8: Calculated specific energy ratio figures
Note on F8: Calculated target consumption using the target equation set in the Phase I.
Note on G8: Calculated difference between the real and target consumption
Note on H8: Cusum of variances between real and target consumption converted to financial dimension using the average utility price from the last year (see. Inputs sheet)

## M&T Area II
Energy management within Area II.
You will implement energy management within Area II (energy consuming unit chosen within screen Inputs).
Monitor outdoor temperature (as degreedays) and related energy consumption within this area weekly.
Enter the data into a new more detailed regression analysis tool here:
Weekly periods | Space heating & DHW
| Consumption | Degree days | SER | Target cons. | Variance | Cumulated savings
| Nm3 | DST | Nm3/DST | Nm3 | Nm3 | € | 2392.8551 | 75.2353
2007-01-01 | 9571 | 111 | 86.2252 | 10743.9737 | 1172.9737 | 346.2861
2007-01-08 | 9235 | 91.5 | 100.929 | 9276.8853 | 41.8853 | 358.6515 | 0 | 2392.8551
2007-01-15 | 10513 | 101.2 | 103.8834 | 10006.6678 | -506.3322 | 209.1718 | 181.5 | 16048.0626
2007-01-22 | 15706 | 162.3 | 96.7714 | 14603.5448 | -1102.4552 | -116.2958
2007-01-29 | 11970 | 126.1 | 94.9247 | 11880.0268 | -89.9732 | -142.8577
2007-02-05 | 12991 | 133.2 | 97.53 | 12414.1975 | -576.8025 | -313.1418
2007-02-12 | 10989 | 114.5 | 95.9738 | 11007.2973 | 18.2973 | -307.74
2007-02-19 | 11371 | 129.8 | 87.604 | 12158.3974 | 787.3974 | -75.284
2007-02-26 | 11219 | 109 | 102.9266 | 10593.5031 | -625.4969 | -259.9436
2007-03-05 | 9961 | 103.9 | 95.871 | 10209.8031 | 248.8031 | -186.4918
2007-03-12 | 10328 | 100.4 | 102.8685 | 9946.4795 | -381.5205 | -299.1245
2007-03-19 | 11502 | 123.5 | 93.1336 | 11684.415 | 182.415 | -245.2718
2007-03-26 | 8762 | 95.4 | 91.8449 | 9570.303 | 808.303 | -6.6441
2007-04-02 | 10544 | 90.6 | 116.3797 | 9209.1736 | -1334.8264 | -400.7124
2007-04-09 | 9371 | 62.8 | 149.2197 | 7117.6321 | -2253.3679 | -1065.9532
2007-04-16 | 7178 | 68.7 | 104.4833 | 7561.5204 | 383.5204 | -952.73
2007-04-23 | 0 | 43.6 | 0 | 5673.1143 | 5673.1143 | 722.0906
2007-04-30 | 0 | 64.6 | 0 | 7253.0557 | 7253.0557 | 2863.3425
2007-05-07 | 0 | 52 | 0 | 6305.0909 | 6305.0909 | 4724.7357
2007-05-14 | 0 | 47.9 | 0 | 5996.6261 | 5996.6261 | 6495.0637
2007-05-21 | 0 | 4.6 | 0 | 2738.9375 | 2738.9375 | 7303.6547
2007-05-28 | 0 | 39 | 0 | 5327.0319 | 5327.0319 | 8876.3046
2007-06-04 | 0 | 15.3 | 0 | 3543.9552 | 3543.9552 | 9922.5535
2007-06-11 | 0 | 4 | 0 | 2693.7963 | 2693.7963 | 10717.8178
2007-06-18 | 0 | 12.1 | 0 | 3303.2023 | 3303.2023 | 11692.9914
2007-06-25 | 0 | 34 | 0 | 4950.8554 | 4950.8554 | 13154.5863
2007-07-02 | 0 | 28.4 | 0 | 4529.5377 | 4529.5377 | 14491.7994
2007-07-09 | 0 | 32.1 | 0 | 4807.9083 | 4807.9083 | 15911.1933
2007-07-16 | 0 | 0 | #N/A | 2392.8551 | 2392.8551 | 16617.6136
2007-07-23 | 0 | 13.8 | 0 | 3431.1023 | 3431.1023 | 17630.546
2007-07-30 | 0 | 31.2 | 0 | 4740.1966 | 4740.1966 | 19029.95
2007-08-06 | 0 | 15.6 | 0 | 3566.5258 | 3566.5258 | 20082.8621
2007-08-13 | 0 | 18.7 | 0 | 3799.7553 | 3799.7553 | 21204.6284
2007-08-20 | 0 | 18.2 | 0 | 3762.1376 | 3762.1376 | 22315.2892
2007-08-27 | 0 | 38.8 | 0 | 5311.9849 | 5311.9849 | 23883.497
2007-09-03 | 653.25 | 64 | 10.207 | 7207.9145 | 6554.6645 | 25818.5694
2007-09-10 | 2228.4 | 62.6 | 35.5974 | 7102.5851 | 4874.1851 | 27257.5296
2007-09-17 | 2128.7 | 60.2 | 35.3605 | 6922.0203 | 4793.3203 | 28672.6169
2007-09-24 | 1914.3 | 65.4 | 29.2706 | 7313.2439 | 5398.9439 | 30266.4967
2007-10-01 | 1413.99 | 60.1 | 23.5273 | 6914.4968 | 5500.5068 | 31890.36
2007-10-08 | 2452.9 | 89 | 27.5607 | 9088.7971 | 6635.8971 | 33849.414
2007-10-15 | 3809.1 | 97.7 | 38.9877 | 9743.3442 | 5934.2442 | 35601.3256
2007-10-22 | 4420.3 | 113.3 | 39.0141 | 10917.0149 | 6496.7149 | 37519.2901
2007-10-29 | 3345.2 | 99.4 | 33.6539 | 9871.2442 | 6526.0442 | 39445.9133
2007-11-05 | 5036.1 | 119.3 | 42.2137 | 11368.4268 | 6332.3268 | 41315.3471
2007-11-12 | 7093.1 | 146.8 | 48.3181 | 13437.3976 | 6344.2976 | 43188.3149
2007-11-19 | 6195.9 | 141.2 | 43.8803 | 13016.0799 | 6820.1799 | 45201.773
2007-11-26 | 7175.1 | 148.8 | 48.2198 | 13587.8682 | 6412.7682 | 47094.9547
2007-12-03 | 4875 | 106.8 | 45.6461 | 10427.9855 | 5552.9855 | 48734.3108
2007-12-10 | 6974.3 | 139.1 | 50.1387 | 12858.0858 | 5883.7858 | 50471.326
2007-12-17 | 9890 | 181.5 | 54.4904 | 16048.0626 | 6158.0626 | 52289.3134
2007-12-24 | 8252.5 | 172 | 47.9797 | 15333.3272 | 7080.8272 | 54379.72
2007-12-31 | 1794 | 41.1 | 43.6496 | 5485.0261 | 3691.0261 | 55469.3872
See results within screen "Deviations"
?
?
Note on B7: Insert labels of weekly time periods
Note on C7: Energy account centre name
Note on C8: Insert corresponding energy account centre consumption
Note on D8: Insert corresponding value of particular influencing factor
Note on E8: Calculated specific energy ratio figures
Note on F8: Calculated target consumption using the target equation set in the Phase I.
Note on G8: Calculated difference between the real and target consumption
Note on H8: Cusum of variances between real and target consumption converted to financial dimension using the average utility price from the last year (see. Inputs sheet)

## Deviations
Energy management - identifying and analysing deviations
Analyse performance of your process and space heating through comparing:
target (red curve representing expected/calculated value of energy consumption for selected variable)
and
actual performance (blue curve of actually measured consumption in specific week)
Process | Space heating & DHW
Any significant variance from the target should lead you to identification of causes of deviations:
WHY DO WE SAVE MONEY IN SOME PERIODS? WHAT WAS DIFFERENT WHEN WE PERFORMED BETTER THAN USUAL?
Fill in identified causes into the screen "Manager"
WHY DO WE WASTE MONEY IN SOME PERIODS? WHAT WAS DIFFERENT WHEN WE PERFORMED WORSE THAN USUAL?
Fill in identified causes into the screen "Manager"
?

## Manager
Energy saving measures manager
Map all significant deviations and identify their causes.
Generate energy saving options and implement feasible measures.
Date | EAC | Deviation / Observation | Cause of deviation / cause of losses or savings | Title of measure | Description | To Do | Deadline | Author | Project leader | Expected annnual saving € | State | Achieved annnual saving €
2007-03-31 | Space heating & DHW | Trend of loses since 12. 3. | Change in heating control system | Heating control system adjustment | Revision and adjustment of the current BMS setup | - Check setup of required temperatures - Propose changes in the setup | 2007-05-01 | PC | Mr. Novak | 500000 | Evaluation
2007-04-16 | Process | Increased electricity consumption in compressor room | Probable losses of compressed air | Silent test on compressed air | Identification of compressed air losses | - Do the silent test - List of identified leaks | 2007-06-01 | PC | Mr. Kucera | 120000 | Implementation
2007-05-30 | Process | repeated savings in gas consumption | Not known yet | No options so far |  | - Observe performance of particular shifts |  |  | Mr. Hajek
Process |  |  |  | Idea
Space heating & DHW |  |  |  | Evaluation
Design
Implementation
Done
Rejected
?

## Continuation
Evaluation and continuation
Evaluate energy performance of your process and space heating through the new lenses of M&T:
Process | Space heating & DHW
Total savings/losses to the date: 7821 € | Total savings/losses to the date: 55469 €
Does M&T add value?
If yes, consider to:
1) extend monitoring to more units (cost centres) through purchasing new monitoring equipment
2) implement a more sophisticated automatic data collection system
3) install sophisticated M&T software for data processing
4) implement system measures to make information from M&T available to your staff influencing energy efficiency
5) make these people accountable for improvement of energy efficiency
6) evaluate results at appropriate levels
7) reflect on experience gained and adopt new policies for further improvement
?

## Example (hidden)
Load User data set | Load User data set | Load example data set | 1 | 2
1 | 3 | 3 | Demonstration project
1 | 5 | 3 | Vanessa Ashley
3 | 6 | 3 | Process
3 | 6 | 4
3 | 6 | 5 | Space heating & DHW
3 | 6 | 6
3 | 6 | 10 | €
3 | 6 | 11
3 | 7 | 10 | 0.637
3 | 8 | 3 | kWh
3 | 8 | 5 | Nm3
3 | 9 | 2 | 2004/1
3 | 9 | 3 | 3233750.5
3 | 9 | 4 | 167302.328
3 | 9 | 5 | 66916.5
3 | 9 | 6 | 13392.96
3 | 10 | 2 | 2004/2
3 | 10 | 3 | 3042366.1
3 | 10 | 4 | 160745.452
3 | 10 | 5 | 64431.2
3 | 10 | 6 | 12937.3176
3 | 11 | 2 | 2004/3
3 | 11 | 3 | 3545457.5
3 | 11 | 4 | 185257.08
3 | 11 | 5 | 58780.4
3 | 11 | 6 | 11840.4684
3 | 12 | 2 | 2004/4
3 | 12 | 3 | 3570384.6
3 | 12 | 4 | 154153.232
3 | 12 | 5 | 47184.3
3 | 12 | 6 | 10493.258
3 | 13 | 2 | 2004/5
3 | 13 | 3 | 3666713.2
3 | 13 | 4 | 152152.348
3 | 13 | 5 | 32985.1
3 | 13 | 6 | 7465.1892
3 | 14 | 2 | 2004/6
3 | 14 | 3 | 3148137.5
3 | 14 | 4 | 144028.492
3 | 14 | 5 | 15715.3
3 | 14 | 6 | 3782.2928
3 | 15 | 2 | 2004/7
3 | 15 | 3 | 3404426.1
3 | 15 | 4 | 149223.684
3 | 15 | 5 | 17690.2
3 | 15 | 6 | 4203.4508
3 | 16 | 2 | 2004/8
3 | 16 | 3 | 3472146.8
3 | 16 | 4 | 152211.192
3 | 16 | 5 | 12075.2
3 | 16 | 6 | 3006.018
3 | 17 | 2 | 2004/9
3 | 17 | 3 | 3197067.2
3 | 17 | 4 | 149954.064
3 | 17 | 5 | 24191.7
3 | 17 | 6 | 5589.9392
3 | 18 | 2 | 2004/10
3 | 18 | 3 | 3259460.2
3 | 18 | 4 | 166672.904
3 | 18 | 5 | 32882.9
3 | 18 | 6 | 7181.48
3 | 19 | 2 | 2004/11
3 | 19 | 3 | 3640018.8
3 | 19 | 4 | 183129.672
3 | 19 | 5 | 54075.4
3 | 19 | 6 | 11532.1612
3 | 20 | 2 | 2004/12
3 | 20 | 3 | 3662697
3 | 20 | 4 | 184365.772
3 | 20 | 5 | 61991.3
3 | 20 | 6 | 13220.316
3 | 21 | 2 | 2005/1
3 | 21 | 3 | 3665758.6
3 | 21 | 4 | 200952.824
3 | 21 | 5 | 68426.3
3 | 21 | 6 | 14447.176
3 | 22 | 2 | 2005/2
3 | 22 | 3 | 3683109.1
3 | 22 | 4 | 201835.672
3 | 22 | 5 | 49009.4
3 | 22 | 6 | 10546.56
3 | 23 | 2 | 2005/3
3 | 23 | 3 | 4269242.1
3 | 23 | 4 | 235967.072
3 | 23 | 5 | 49632.6
3 | 23 | 6 | 10671.76
3 | 24 | 2 | 2005/4
3 | 24 | 3 | 4064433.1
3 | 24 | 4 | 223152.24
3 | 24 | 5 | 36089
3 | 24 | 6 | 7637.632
3 | 25 | 2 | 2005/5
3 | 25 | 3 | 3784107.5
3 | 25 | 4 | 213794.352
3 | 25 | 5 | 29954.3
3 | 25 | 6 | 6457.84
3 | 26 | 2 | 2005/6
3 | 26 | 3 | 3906042.6
3 | 26 | 4 | 225753.972
3 | 26 | 5 | 20588
3 | 26 | 6 | 4657.848
3 | 27 | 2 | 2005/7
3 | 27 | 3 | 4078967.1
3 | 27 | 4 | 238720.332
3 | 27 | 5 | 19724.4
3 | 27 | 6 | 4491.904
3 | 28 | 2 | 2005/8
3 | 28 | 3 | 4245918.9
3 | 28 | 4 | 234295.376
3 | 28 | 5 | 11204.6
3 | 28 | 6 | 2854.56
3 | 29 | 2 | 2005/9
3 | 29 | 3 | 3978876
3 | 29 | 4 | 218849.484
3 | 29 | 5 | 47330.3
3 | 29 | 6 | 9797.16
3 | 30 | 2 | 2005/10
3 | 30 | 3 | 4094073
3 | 30 | 4 | 223582.572
3 | 30 | 5 | 37512.5
3 | 30 | 6 | 8953.532
3 | 31 | 2 | 2005/11
3 | 31 | 3 | 4260130.4
3 | 31 | 4 | 231958.536
3 | 31 | 5 | 49596.9
3 | 31 | 6 | 11611.94
3 | 32 | 2 | 2005/12
3 | 32 | 3 | 4184127.9
3 | 32 | 4 | 228603.864
3 | 32 | 5 | 63263.4
3 | 32 | 6 | 14618.396
3 | 33 | 2 | 2006/1
3 | 33 | 3 | 3771852.5
3 | 33 | 4 | 231557.156
3 | 33 | 5 | 60022.5833
3 | 33 | 6 | 16029.84
3 | 34 | 2 | 2006/2
3 | 34 | 3 | 3645806.6
3 | 34 | 4 | 226481.344
3 | 34 | 5 | 63769.975
3 | 34 | 6 | 17096.76
3 | 35 | 2 | 2006/3
3 | 35 | 3 | 4017984.5
3 | 35 | 4 | 249177.456
3 | 35 | 5 | 55087.225
3 | 35 | 6 | 14857.56
3 | 36 | 2 | 2006/4
3 | 36 | 3 | 3370254
3 | 36 | 4 | 209845.788
3 | 36 | 5 | 32842.1708
3 | 36 | 6 | 8972.04
3 | 37 | 2 | 2006/5
3 | 37 | 3 | 3398793.1
3 | 37 | 4 | 213764.648
3 | 37 | 5 | 26232.6875
3 | 37 | 6 | 7324.56
3 | 38 | 2 | 2006/6
3 | 38 | 3 | 3382749.8
3 | 38 | 4 | 214831.36
3 | 38 | 5 | 19405.6625
3 | 38 | 6 | 5631.48
3 | 39 | 2 | 2006/7
3 | 39 | 3 | 3372468.5
3 | 39 | 4 | 209288.744
3 | 39 | 5 | 16896.3667
3 | 39 | 6 | 5241.76
3 | 40 | 2 | 2006/8
3 | 40 | 3 | 3568355
3 | 40 | 4 | 226725.744
3 | 40 | 5 | 16741.25
3 | 40 | 6 | 5194.64
3 | 41 | 2 | 2006/9
3 | 41 | 3 | 3572599.1
3 | 41 | 4 | 224612.812
3 | 41 | 5 | 18777.6292
3 | 41 | 6 | 5724.08
3 | 42 | 2 | 2006/10
3 | 42 | 3 | 3648240.4
3 | 42 | 4 | 223257.708
3 | 42 | 5 | 29735.1083
3 | 42 | 6 | 10270.08
3 | 43 | 2 | 2006/11
3 | 43 | 3 | 3947412.9
3 | 43 | 4 | 241412.68
3 | 43 | 5 | 47146.0083
3 | 43 | 6 | 15814.92
3 | 44 | 2 | 2006/12
3 | 44 | 3 | 3742011
3 | 44 | 4 | 229015.584
3 | 44 | 5 | 50999
3 | 44 | 6 | 17047.28
4 | 7 | 4 | Production
4 | 8 | 4 | t
4 | 9 | 4 | 20720
4 | 10 | 4 | 20368
4 | 11 | 4 | 22648
4 | 12 | 4 | 22187
4 | 13 | 4 | 22913
4 | 14 | 4 | 18789
4 | 15 | 4 | 23618
4 | 16 | 4 | 25714
4 | 17 | 4 | 22211
4 | 18 | 4 | 22965
4 | 19 | 4 | 24859
4 | 20 | 4 | 22466
4 | 21 | 4 | 24809
4 | 22 | 4 | 25027
4 | 23 | 4 | 27840
4 | 24 | 4 | 27630
4 | 25 | 4 | 26330
4 | 26 | 4 | 25424
4 | 27 | 4 | 25964
4 | 28 | 4 | 27050
4 | 29 | 4 | 27020
4 | 30 | 4 | 26655
4 | 31 | 4 | 27190
4 | 32 | 4 | 26000
4 | 33 | 4 | 27422
4 | 34 | 4 | 25074
4 | 35 | 4 | 28316
4 | 36 | 4 | 24820
4 | 37 | 4 | 23880
4 | 38 | 4 | 24170
4 | 39 | 4 | 24960
4 | 40 | 4 | 24750
4 | 41 | 4 | 22660
4 | 42 | 4 | 26655
4 | 43 | 4 | 27050
4 | 44 | 4 | 25760
5 | 7 | 4 | Degree days
5 | 8 | 4 | DST
5 | 9 | 4 | 712.6
5 | 10 | 4 | 693.8
5 | 11 | 4 | 519.6
5 | 12 | 4 | 405.2
5 | 13 | 4 | 185.4
5 | 14 | 4 | 54.4
5 | 15 | 4 | 84.8
5 | 16 | 4 | 50.2
5 | 17 | 4 | 220.8
5 | 18 | 4 | 495.3
5 | 19 | 4 | 512.5
5 | 20 | 4 | 662.2
5 | 21 | 4 | 751.2
5 | 22 | 4 | 558.5
5 | 23 | 4 | 545.4
5 | 24 | 4 | 349.1
5 | 25 | 4 | 279.2
5 | 26 | 4 | 150.3
5 | 27 | 4 | 98.9
5 | 28 | 4 | 76.9
5 | 29 | 4 | 213.1
5 | 30 | 4 | 360.9
5 | 31 | 4 | 527.1
5 | 32 | 4 | 665.8
5 | 33 | 4 | 635.2
5 | 34 | 4 | 677.4
5 | 35 | 4 | 583.6
5 | 36 | 4 | 337.3
5 | 37 | 4 | 231.6
5 | 38 | 4 | 121.8
5 | 39 | 4 | 97.9
5 | 40 | 4 | 139.9
5 | 41 | 4 | 186.1
5 | 42 | 4 | 348.9
5 | 43 | 4 | 561.9
5 | 44 | 4 | 670.3
6 | 8 | 2 | Electricity - 3-phase meter incl. CTs
6 | 8 | 4 | 15
6 | 9 | 2 | Cold water - DN50 turbine
6 | 9 | 4 | 3
6 | 10 | 2 | Natural gas - DN100
6 | 10 | 4 | 5
6 | 11 | 2 | Cold water - DN200 turbine
6 | 11 | 4 | 2
6 | 12 | 2 | Steam - DN50 orifice plate
6 | 12 | 4 | 4
6 | 13 | 2 | Cold water - DN100 turbine
6 | 13 | 4 | 4
6 | 14 | 2
6 | 14 | 4
6 | 15 | 2
6 | 15 | 4
6 | 16 | 2
6 | 16 | 4
6 | 17 | 2
6 | 17 | 4
6 | 18 | 2
6 | 18 | 4
6 | 19 | 2
6 | 19 | 4
6 | 20 | 2
6 | 20 | 4
6 | 21 | 2
6 | 21 | 4
6 | 22 | 2
6 | 22 | 4
6 | 24 | 5 | 10000
6 | 25 | 5 | 1932-11-07
6 | 26 | 5 | 1949-04-12
6 | 34 | 4 | 1900-01-09
7 | 10 | 2 | 2007-01-01
7 | 10 | 3 | 727095.7484
7 | 10 | 4 | 1910-05-18
7 | 11 | 2 | 2007-01-08
7 | 11 | 3 | 802061.6968
7 | 11 | 4 | 1920-07-14
7 | 12 | 2 | 2007-01-15
7 | 12 | 3 | 904960.5104
7 | 12 | 4 | 1920-08-12
7 | 13 | 2 | 2007-01-22
7 | 13 | 3 | 858397.1694
7 | 13 | 4 | 1918-08-05
7 | 14 | 2 | 2007-01-29
7 | 14 | 3 | 879516.0009
7 | 14 | 4 | 1914-09-09
7 | 15 | 2 | 2007-02-05
7 | 15 | 3 | 1012356.2353
7 | 15 | 4 | 1916-11-12
7 | 16 | 2 | 2007-02-12
7 | 16 | 3 | 519569.4084
7 | 16 | 4 | 1911-01-14
7 | 17 | 2 | 2007-02-19
7 | 17 | 3 | 829805.8918
7 | 17 | 4 | 1913-12-11
7 | 18 | 2 | 2007-02-26
7 | 18 | 3 | 1034878.3396
7 | 18 | 4 | 1924-01-27
7 | 19 | 2 | 2007-03-05
7 | 19 | 3 | 1378681.3276
7 | 19 | 4 | 1924-05-13
7 | 20 | 2 | 2007-03-12
7 | 20 | 3 | 1190863.4919
7 | 20 | 4 | 1920-06-24
7 | 21 | 2 | 2007-03-19
7 | 21 | 3 | 1029624.249
7 | 21 | 4 | 1919-07-29
7 | 22 | 2 | 2007-03-26
7 | 22 | 3 | 759197.9229
7 | 22 | 4 | 1909-09-17
7 | 23 | 2 | 2007-04-02
7 | 23 | 3 | 1026099.0322
7 | 23 | 4 | 1915-02-24
7 | 24 | 2 | 2007-04-09
7 | 24 | 3 | 1401709.9041
7 | 24 | 4 | 1927-04-14
7 | 25 | 2 | 2007-04-16
7 | 25 | 3 | 834500.9114
7 | 25 | 4 | 1919-05-23
7 | 26 | 2 | 2007-04-23
7 | 26 | 3 | 1312973.4332
7 | 26 | 4 | 1922-07-22
7 | 27 | 2 | 2007-04-30
7 | 27 | 3 | 981440.4992
7 | 27 | 4 | 1925-03-12
7 | 28 | 2 | 2007-05-07
7 | 28 | 3 | 1290224.3978
7 | 28 | 4 | 1923-03-21
7 | 29 | 2 | 2007-05-14
7 | 29 | 3 | 652093.3349
7 | 29 | 4 | 1909-09-30
7 | 30 | 2 | 2007-05-21
7 | 30 | 3 | 862924.2768
7 | 30 | 4 | 1914-09-20
7 | 31 | 2 | 2007-05-28
7 | 31 | 3 | 831574.5798
7 | 31 | 4 | 1912-11-26
7 | 32 | 2 | 2007-06-04
7 | 32 | 3 | 1020255.2829
7 | 32 | 4 | 1921-09-10
7 | 33 | 2 | 2007-06-11
7 | 33 | 3 | 715407.4956
7 | 33 | 4 | 1916-04-09
7 | 34 | 2 | 2007-06-18
7 | 34 | 3 | 939207.7661
7 | 34 | 4 | 1921-06-10
7 | 35 | 2 | 2007-06-25
7 | 35 | 3 | 756369.0658
7 | 35 | 4 | 1918-09-02
7 | 36 | 2 | 2007-07-02
7 | 36 | 3 | 837592.7642
7 | 36 | 4 | 1915-05-02
7 | 37 | 2 | 2007-07-09
7 | 37 | 3 | 1078530.6381
7 | 37 | 4 | 1923-03-07
7 | 38 | 2 | 2007-07-16
7 | 38 | 3 | 901782.5673
7 | 38 | 4 | 1912-03-06
7 | 39 | 2 | 2007-07-23
7 | 39 | 3 | 1304427.4327
7 | 39 | 4 | 1924-09-05
7 | 40 | 2 | 2007-07-30
7 | 40 | 3 | 657090.6458
7 | 40 | 4 | 1910-07-07
7 | 41 | 2 | 2007-08-06
7 | 41 | 3 | 1611044.5221
7 | 41 | 4 | 1928-10-01
7 | 42 | 2 | 2007-08-13
7 | 42 | 3 | 1034132.514
7 | 42 | 4 | 1921-06-08
7 | 43 | 2 | 2007-08-20
7 | 43 | 3 | 1298037.9521
7 | 43 | 4 | 1921-12-31
7 | 44 | 2 | 2007-08-27
7 | 44 | 3 | 1024971.3288
7 | 44 | 4 | 1920-03-08
7 | 45 | 2 | 2007-09-03
7 | 45 | 3 | 741465.0635
7 | 45 | 4 | 1912-11-28
7 | 46 | 2 | 2007-09-10
7 | 46 | 3 | 962318.1811
7 | 46 | 4 | 1919-04-18
7 | 47 | 2 | 2007-09-17
7 | 47 | 3 | 1124145.7584
7 | 47 | 4 | 1920-09-29
7 | 48 | 2 | 2007-09-24
7 | 48 | 3 | 861832.967
7 | 48 | 4 | 1919-12-28
7 | 49 | 2 | 2007-10-01
7 | 49 | 3 | 718706.8673
7 | 49 | 4 | 1912-11-17
7 | 50 | 2 | 2007-10-08
7 | 50 | 3 | 1594406.6305
7 | 50 | 4 | 1926-05-28
7 | 51 | 2 | 2007-10-15
7 | 51 | 3 | 1620255.7079
7 | 51 | 4 | 1929-06-18
7 | 52 | 2 | 2007-10-22
7 | 52 | 3 | 1228239.2614
7 | 52 | 4 | 1929-04-24
7 | 53 | 2 | 2007-10-29
7 | 53 | 3 | 932333.0531
7 | 53 | 4 | 1926-08-22
7 | 54 | 2 | 2007-11-05
7 | 54 | 3 | 813124.1722
7 | 54 | 4 | 1911-04-05
7 | 55 | 2 | 2007-11-12
7 | 55 | 3 | 450930.896
7 | 55 | 4 | 1910-03-22
7 | 56 | 2 | 2007-11-19
7 | 56 | 3 | 527917.4643
7 | 56 | 4 | 1911-03-26
7 | 57 | 2 | 2007-11-26
7 | 57 | 3 | 1713113.5489
7 | 57 | 4 | 1929-08-28
7 | 58 | 2 | 2007-12-03
7 | 58 | 3 | 1171003.0154
7 | 58 | 4 | 1925-10-01
7 | 59 | 2 | 2007-12-10
7 | 59 | 3 | 939682.3762
7 | 59 | 4 | 1915-05-05
7 | 60 | 2 | 2007-12-17
7 | 60 | 3 | 1048882.8211
7 | 60 | 4 | 1916-08-27
7 | 61 | 2 | 2007-12-24
7 | 61 | 3 | 775665.078
7 | 61 | 4 | 1913-07-05
7 | 62 | 2 | 2007-12-31
7 | 62 | 3 | 1121265.6086
7 | 62 | 4 | 1925-04-27
8 | 10 | 2 | 2007-01-01
8 | 10 | 3 | 1926-03-15
8 | 10 | 4 | 1900-04-20
8 | 11 | 2 | 2007-01-08
8 | 11 | 3 | 1925-04-13
8 | 11 | 4 | 1900-03-31 12:00
8 | 12 | 2 | 2007-01-15
8 | 12 | 3 | 1928-10-12
8 | 12 | 4 | 1900-04-10 04:48
8 | 13 | 2 | 2007-01-22
8 | 13 | 3 | 1942-12-31
8 | 13 | 4 | 1900-06-10 07:12
8 | 14 | 2 | 2007-01-29
8 | 14 | 3 | 1932-10-08
8 | 14 | 4 | 1900-05-05 02:24
8 | 15 | 2 | 2007-02-05
8 | 15 | 3 | 1935-07-26
8 | 15 | 4 | 1900-05-12 04:48
8 | 16 | 2 | 2007-02-12
8 | 16 | 3 | 1930-01-31
8 | 16 | 4 | 1900-04-23 12:00
8 | 17 | 2 | 2007-02-19
8 | 17 | 3 | 1931-02-17
8 | 17 | 4 | 1900-05-08 19:12
8 | 18 | 2 | 2007-02-26
8 | 18 | 3 | 1930-09-18
8 | 18 | 4 | 1900-04-18
8 | 19 | 2 | 2007-03-05
8 | 19 | 3 | 1927-04-09
8 | 19 | 4 | 1900-04-12 21:36
8 | 20 | 2 | 2007-03-12
8 | 20 | 3 | 1928-04-10
8 | 20 | 4 | 1900-04-09 09:36
8 | 21 | 2 | 2007-03-19
8 | 21 | 3 | 1931-06-28
8 | 21 | 4 | 1900-05-02 12:00
8 | 22 | 2 | 2007-03-26
8 | 22 | 3 | 1923-12-27
8 | 22 | 4 | 1900-04-04 09:36
8 | 23 | 2 | 2007-04-02
8 | 23 | 3 | 1928-11-12
8 | 23 | 4 | 1900-03-30 14:24
8 | 24 | 2 | 2007-04-09
8 | 24 | 3 | 1925-08-27
8 | 24 | 4 | 1900-03-02 19:12
8 | 25 | 2 | 2007-04-16
8 | 25 | 3 | 1919-08-26
8 | 25 | 4 | 1900-03-08 16:48
8 | 26 | 2 | 2007-04-23
8 | 26 | 3 | 0
8 | 26 | 4 | 1900-02-11 14:24
8 | 27 | 2 | 2007-04-30
8 | 27 | 3 | 0
8 | 27 | 4 | 1900-03-04 14:24
8 | 28 | 2 | 2007-05-07
8 | 28 | 3 | 0
8 | 28 | 4 | 1900-02-20
8 | 29 | 2 | 2007-05-14
8 | 29 | 3 | 0
8 | 29 | 4 | 1900-02-15 21:36
8 | 30 | 2 | 2007-05-21
8 | 30 | 3 | 0
8 | 30 | 4 | 1900-01-03 14:24
8 | 31 | 2 | 2007-05-28
8 | 31 | 3 | 0
8 | 31 | 4 | 1900-02-07
8 | 32 | 2 | 2007-06-04
8 | 32 | 3 | 0
8 | 32 | 4 | 1900-01-14 07:12
8 | 33 | 2 | 2007-06-11
8 | 33 | 3 | 0
8 | 33 | 4 | 1900-01-03
8 | 34 | 2 | 2007-06-18
8 | 34 | 3 | 0
8 | 34 | 4 | 1900-01-11 02:24
8 | 35 | 2 | 2007-06-25
8 | 35 | 3 | 0
8 | 35 | 4 | 1900-02-02
8 | 36 | 2 | 2007-07-02
8 | 36 | 3 | 0
8 | 36 | 4 | 1900-01-27 09:36
8 | 37 | 2 | 2007-07-09
8 | 37 | 3 | 0
8 | 37 | 4 | 1900-01-31 02:24
8 | 38 | 2 | 2007-07-16
8 | 38 | 3 | 0
8 | 38 | 4 | 0
8 | 39 | 2 | 2007-07-23
8 | 39 | 3 | 0
8 | 39 | 4 | 1900-01-12 19:12
8 | 40 | 2 | 2007-07-30
8 | 40 | 3 | 0
8 | 40 | 4 | 1900-01-30 04:48
8 | 41 | 2 | 2007-08-06
8 | 41 | 3 | 0
8 | 41 | 4 | 1900-01-14 14:24
8 | 42 | 2 | 2007-08-13
8 | 42 | 3 | 0
8 | 42 | 4 | 1900-01-17 16:48
8 | 43 | 2 | 2007-08-20
8 | 43 | 3 | 0
8 | 43 | 4 | 1900-01-17 04:48
8 | 44 | 2 | 2007-08-27
8 | 44 | 3 | 0
8 | 44 | 4 | 1900-02-06 19:12
8 | 45 | 2 | 2007-09-03
8 | 45 | 3 | 1901-10-14 06:00
8 | 45 | 4 | 1900-03-04
8 | 46 | 2 | 2007-09-10
8 | 46 | 3 | 1906-02-05 09:36
8 | 46 | 4 | 1900-03-02 14:24
8 | 47 | 2 | 2007-09-17
8 | 47 | 3 | 1905-10-28 16:48
8 | 47 | 4 | 1900-02-28 04:48
8 | 48 | 2 | 2007-09-24
8 | 48 | 3 | 1905-03-28 07:12
8 | 48 | 4 | 1900-03-05 09:36
8 | 49 | 2 | 2007-10-01
8 | 49 | 3 | 1903-11-13 23:46
8 | 49 | 4 | 1900-02-28 02:24
8 | 50 | 2 | 2007-10-08
8 | 50 | 3 | 1906-09-17 21:36
8 | 50 | 4 | 1900-03-29
8 | 51 | 2 | 2007-10-15
8 | 51 | 3 | 1910-06-05 02:24
8 | 51 | 4 | 1900-04-06 16:48
8 | 52 | 2 | 2007-10-22
8 | 52 | 3 | 1912-02-06 07:12
8 | 52 | 4 | 1900-04-22 07:12
8 | 53 | 2 | 2007-10-29
8 | 53 | 3 | 1909-02-26 04:48
8 | 53 | 4 | 1900-04-08 09:36
8 | 54 | 2 | 2007-11-05
8 | 54 | 3 | 1913-10-14 02:24
8 | 54 | 4 | 1900-04-28 07:12
8 | 55 | 2 | 2007-11-12
8 | 55 | 3 | 1919-06-02 02:24
8 | 55 | 4 | 1900-05-25 19:12
8 | 56 | 2 | 2007-11-19
8 | 56 | 3 | 1916-12-16 21:36
8 | 56 | 4 | 1900-05-20 04:48
8 | 57 | 2 | 2007-11-26
8 | 57 | 3 | 1919-08-23 02:24
8 | 57 | 4 | 1900-05-27 19:12
8 | 58 | 2 | 2007-12-03
8 | 58 | 3 | 1913-05-06
8 | 58 | 4 | 1900-04-15 19:12
8 | 59 | 2 | 2007-12-10
8 | 59 | 3 | 1919-02-03 07:12
8 | 59 | 4 | 1900-05-18 02:24
8 | 60 | 2 | 2007-12-17
8 | 60 | 3 | 1927-01-28
8 | 60 | 4 | 1900-06-29 12:00
8 | 61 | 2 | 2007-12-24
8 | 61 | 3 | 1922-08-04 12:00
8 | 61 | 4 | 1900-06-20
8 | 62 | 2 | 2007-12-31
8 | 62 | 3 | 1904-11-28
8 | 62 | 4 | 1900-02-09 02:24
10 | 7 | 2 | 2007-03-31
10 | 7 | 3 | Space heating & DHW
10 | 7 | 4 | Trend of loses since 12. 3.
10 | 7 | 5 | Change in heating control system
10 | 7 | 6 | Heating control system adjustment
10 | 7 | 7 | Revision and adjustment of the current BMS setup
10 | 7 | 8 | - Check setup of required temperatures - Propose changes in the setup
10 | 7 | 9 | 2007-05-01
10 | 7 | 10 | PC
10 | 7 | 11 | Mr. Novak
10 | 7 | 12 | 500000
10 | 7 | 13 | Evaluation
10 | 7 | 14
10 | 8 | 2 | 2007-04-16
10 | 8 | 3 | Process
10 | 8 | 4 | Increased electricity consumption in compressor room
10 | 8 | 5 | Probable losses of compressed air
10 | 8 | 6 | Silent test on compressed air
10 | 8 | 7 | Identification of compressed air losses
10 | 8 | 8 | - Do the silent test - List of identified leaks
10 | 8 | 9 | 2007-06-01
10 | 8 | 10 | PC
10 | 8 | 11 | Mr. Kucera
10 | 8 | 12 | 2228-07-18
10 | 8 | 13 | Implementation
10 | 8 | 14
10 | 9 | 2 | 2007-05-30
10 | 9 | 3 | Process
10 | 9 | 4 | repeated savings in gas consumption
10 | 9 | 5 | Not known yet
10 | 9 | 6 | No options so far
10 | 9 | 7
10 | 9 | 8 | - Observe performance of particular shifts
10 | 9 | 9
10 | 9 | 10
10 | 9 | 11 | Mr. Hajek
10 | 9 | 12
10 | 9 | 13
10 | 9 | 14
10 | 10 | 2
10 | 10 | 3
10 | 10 | 4
10 | 10 | 5
10 | 10 | 6
10 | 10 | 7
10 | 10 | 8
10 | 10 | 9
10 | 10 | 10
10 | 10 | 11
10 | 10 | 12
10 | 10 | 13
10 | 10 | 14
10 | 11 | 2
10 | 11 | 3
10 | 11 | 4
10 | 11 | 5
10 | 11 | 6
10 | 11 | 7
10 | 11 | 8
10 | 11 | 9
10 | 11 | 10
10 | 11 | 11
10 | 11 | 12
10 | 11 | 13
10 | 11 | 14
10 | 12 | 2
10 | 12 | 3
10 | 12 | 4
10 | 12 | 5
10 | 12 | 6
10 | 12 | 7
10 | 12 | 8
10 | 12 | 9
10 | 12 | 10
10 | 12 | 11
10 | 12 | 12
10 | 12 | 13
10 | 12 | 14
10 | 13 | 2
10 | 13 | 3
10 | 13 | 4
10 | 13 | 5
10 | 13 | 6
10 | 13 | 7
10 | 13 | 8
10 | 13 | 9
10 | 13 | 10
10 | 13 | 11
10 | 13 | 12
10 | 13 | 13
10 | 13 | 14
10 | 14 | 2
10 | 14 | 3
10 | 14 | 4
10 | 14 | 5
10 | 14 | 6
10 | 14 | 7
10 | 14 | 8
10 | 14 | 9
10 | 14 | 10
10 | 14 | 11
10 | 14 | 12
10 | 14 | 13
10 | 14 | 14
10 | 15 | 2
10 | 15 | 3
10 | 15 | 4
10 | 15 | 5
10 | 15 | 6
10 | 15 | 7
10 | 15 | 8
10 | 15 | 9
10 | 15 | 10
10 | 15 | 11
10 | 15 | 12
10 | 15 | 13
10 | 15 | 14
10 | 16 | 2
10 | 16 | 3
10 | 16 | 4
10 | 16 | 5
10 | 16 | 6
10 | 16 | 7
10 | 16 | 8
10 | 16 | 9
10 | 16 | 10
10 | 16 | 11
10 | 16 | 12
10 | 16 | 13
10 | 16 | 14
10 | 17 | 2
10 | 17 | 3
10 | 17 | 4
10 | 17 | 5
10 | 17 | 6
10 | 17 | 7
10 | 17 | 8
10 | 17 | 9
10 | 17 | 10
10 | 17 | 11
10 | 17 | 12
10 | 17 | 13
10 | 17 | 14
10 | 18 | 2
10 | 18 | 3
10 | 18 | 4
10 | 18 | 5
10 | 18 | 6
10 | 18 | 7
10 | 18 | 8
10 | 18 | 9
10 | 18 | 10
10 | 18 | 11
10 | 18 | 12
10 | 18 | 13
10 | 18 | 14
10 | 19 | 2
10 | 19 | 3
10 | 19 | 4
10 | 19 | 5
10 | 19 | 6
10 | 19 | 7
10 | 19 | 8
10 | 19 | 9
10 | 19 | 10
10 | 19 | 11
10 | 19 | 12
10 | 19 | 13
10 | 19 | 14
10 | 20 | 2
10 | 20 | 3
10 | 20 | 4
10 | 20 | 5
10 | 20 | 6
10 | 20 | 7
10 | 20 | 8
10 | 20 | 9
10 | 20 | 10
10 | 20 | 11
10 | 20 | 12
10 | 20 | 13
10 | 20 | 14
10 | 21 | 2
10 | 21 | 3
10 | 21 | 4
10 | 21 | 5
10 | 21 | 6
10 | 21 | 7
10 | 21 | 8
10 | 21 | 9
10 | 21 | 10
10 | 21 | 11
10 | 21 | 12
10 | 21 | 13
10 | 21 | 14
10 | 22 | 2
10 | 22 | 3
10 | 22 | 4
10 | 22 | 5
10 | 22 | 6
10 | 22 | 7
10 | 22 | 8
10 | 22 | 9
10 | 22 | 10
10 | 22 | 11
10 | 22 | 12
10 | 22 | 13
10 | 22 | 14
10 | 23 | 2
10 | 23 | 3
10 | 23 | 4
10 | 23 | 5
10 | 23 | 6
10 | 23 | 7
10 | 23 | 8
10 | 23 | 9
10 | 23 | 10
10 | 23 | 11
10 | 23 | 12
10 | 23 | 13
10 | 23 | 14
10 | 24 | 2
10 | 24 | 3
10 | 24 | 4
10 | 24 | 5
10 | 24 | 6
10 | 24 | 7
10 | 24 | 8
10 | 24 | 9
10 | 24 | 10
10 | 24 | 11
10 | 24 | 12
10 | 24 | 13
10 | 24 | 14
10 | 25 | 2
10 | 25 | 3
10 | 25 | 4
10 | 25 | 5
10 | 25 | 6
10 | 25 | 7
10 | 25 | 8
10 | 25 | 9
10 | 25 | 10
10 | 25 | 11
10 | 25 | 12
10 | 25 | 13
10 | 25 | 14
10 | 26 | 2
10 | 26 | 3
10 | 26 | 4
10 | 26 | 5
10 | 26 | 6
10 | 26 | 7
10 | 26 | 8
10 | 26 | 9
10 | 26 | 10
10 | 26 | 11
10 | 26 | 12
10 | 26 | 13
10 | 26 | 14
10 | 27 | 2
10 | 27 | 3
10 | 27 | 4
10 | 27 | 5
10 | 27 | 6
10 | 27 | 7
10 | 27 | 8
10 | 27 | 9
10 | 27 | 10
10 | 27 | 11
10 | 27 | 12
10 | 27 | 13
10 | 27 | 14
10 | 28 | 2
10 | 28 | 3
10 | 28 | 4
10 | 28 | 5
10 | 28 | 6
10 | 28 | 7
10 | 28 | 8
10 | 28 | 9
10 | 28 | 10
10 | 28 | 11
10 | 28 | 12
10 | 28 | 13
10 | 28 | 14
10 | 29 | 2
10 | 29 | 3
10 | 29 | 4
10 | 29 | 5
10 | 29 | 6
10 | 29 | 7
10 | 29 | 8
10 | 29 | 9
10 | 29 | 10
10 | 29 | 11
10 | 29 | 12
10 | 29 | 13
10 | 29 | 14
10 | 30 | 2
10 | 30 | 3
10 | 30 | 4
10 | 30 | 5
10 | 30 | 6
10 | 30 | 7
10 | 30 | 8
10 | 30 | 9
10 | 30 | 10
10 | 30 | 11
10 | 30 | 12
10 | 30 | 13
10 | 30 | 14
10 | 31 | 2
10 | 31 | 3
10 | 31 | 4
10 | 31 | 5
10 | 31 | 6
10 | 31 | 7
10 | 31 | 8
10 | 31 | 9
10 | 31 | 10
10 | 31 | 11
10 | 31 | 12
10 | 31 | 13
10 | 31 | 14
10 | 32 | 2
10 | 32 | 3
10 | 32 | 4
10 | 32 | 5
10 | 32 | 6
10 | 32 | 7
10 | 32 | 8
10 | 32 | 9
10 | 32 | 10
10 | 32 | 11
10 | 32 | 12
10 | 32 | 13
10 | 32 | 14
10 | 33 | 2
10 | 33 | 3
10 | 33 | 4
10 | 33 | 5
10 | 33 | 6
10 | 33 | 7
10 | 33 | 8
10 | 33 | 9
10 | 33 | 10
10 | 33 | 11
10 | 33 | 12
10 | 33 | 13
10 | 33 | 14
10 | 34 | 2
10 | 34 | 3
10 | 34 | 4
10 | 34 | 5
10 | 34 | 6
10 | 34 | 7
10 | 34 | 8
10 | 34 | 9
10 | 34 | 10
10 | 34 | 11
10 | 34 | 12
10 | 34 | 13
10 | 34 | 14
10 | 35 | 2
10 | 35 | 3
10 | 35 | 4
10 | 35 | 5
10 | 35 | 6
10 | 35 | 7
10 | 35 | 8
10 | 35 | 9
10 | 35 | 10
10 | 35 | 11
10 | 35 | 12
10 | 35 | 13
10 | 35 | 14
10 | 36 | 2
10 | 36 | 3
10 | 36 | 4
10 | 36 | 5
10 | 36 | 6
10 | 36 | 7
10 | 36 | 8
10 | 36 | 9
10 | 36 | 10
10 | 36 | 11
10 | 36 | 12
10 | 36 | 13
10 | 36 | 14

## Case study
Case study
A company producing construction materials faced increasing production costs. The company used to consider the cost of energy inputs as a fixed budget item. Increase of energy prices made the company management to question this assumption.
Phase I
Inputs
The company started review of its energy management by analysing its historical energy bills from the last three years. The energy balance developed using the available data enabled to trace the historical consumption curves. Even such a basic analysis led to new understanding of consumption patterns and fluctuations in actual energy costs It led to new questions and showed promising scope for more detailed investigations.
Potential for savings
For more precise evaluation of company performance within the field of energy efficiency more information was needed. Additional data sets describing most important variables influencing energy consumption were needed in order to track actual energy efficiency. First, the set of heating degree days was analysed which describe the real need of natural gas for space heating and domestic hot water preparation. Second, the overall production volume was identified as the best variable describing real need for electricity (as most of it is used directly in the production process).
An analysis was carried out of dependence between energy consumption and these two independent variables based on additional information filled in to screens Savings Area I and Savings Area II. Results were expressed mathematically and graphically: In the scatter plot graphs are displaying best fit lines representing statistical dependence of energy consumption related to the relevant variable (as a result of linear regression analysis). This mathematical expression of dependence of energy consumption on relevant variables is used for evaluation of achieved energy efficiency performance later and within M&T this is called the "target".
The company was not equipped with a sub-metering system enabling deeper investigations needed for identification and evaluation of particular energy saving measures. The main objective of the undertaken analysis was evaluation of the scope of energy saving potential as an inevitable input for decisions on next steps. The potential for savings was evaluated in a simplified way based on the assumption that energy consumption exceeding the statistical dependence of energy consumption on relevant the variable (best fit line) could be easily avoided within the existing processes and represents wasting of energy (potential for savings). This over-consumption is quantified by a simple sum over the given period of time.
M&T Feasibility
The proper M&T system usually goes deeper and splits energy consumption within the company to smaller parts where it is easier and more accurate to set up the best fit lines (targets). The important prerequisite of such approach is a sub-metering system. The system provides better data useful for M&T analysis. However, it comes at a certain cost. Therefore it is necessary to evaluate whether the investment is reasonable or not. It should be reviewed as a standard investment opportunity with calculation of common parameters as the pay-back period, net present value, investment rate of return etc.
Results of the "feasibility study" were in our case promising - the simple pay back period was 1,2 year as can be seen within the screen Feasibility. Therefore management decided to extend the sub-metering system including automatic data collection and to use a specialized M&T software. The M&T software facilitates analysing, sharing and reporting energy efficiency related data and enables users to manage energy flows within company effectively. However, we go back to the simple M&T Tool and experience from its use within our case study.
Phase II
M&T Area
Our company selected two energy consuming units (cost centres) within "M&T Area I" and "M&T Area II" for more detailed investigation. The site energy manager started data collection on weekly basis for better control of energy efficiency within these areas. Results of weekly performance are displayed in the scatter plot graphs on sheets "M&T Area I" and "M&T Area II". The red line displays results of previous regression analysis based on historical monthly data (this line represents a baseline - theoretical target of energy efficiency performance at the very beginning).
Regression analysis is calculated automatically by the M&T Tool and showed deviation from expected performance and therefore a potential for savings within the area of space heating. Based on this analysis and local investigation, options were generated for improvement of overall efficiency of the heating system and the system for preparation of domestic hot water. The feasible measures were implemented during summer season 2007 and their positive impact is visible on the screen "M&T Area II". The blue points below the best fit line correspond to the beginning of heating season 2007-08.
Identification of energy conservation measures was much more complicated within the area of process related electricity consumption within the case study so far. Available data include consumption of the number of users and production lines. No sub-metering system was available at that time. However, achievements in the heating area convinced the management to start proposed M&T implementation including installation of a sub-metering system. It will make the analysis more precise and easier.
Deviations
The M&T methodology uses different views on the data to help to understand patterns and dependencies in the energy consuming processes as this understanding is the first step to managing the process and its energy efficiency. Several of the often used graphs are available within the screen "Deviations". The "Actual and Target" graph compares the real measured consumption data with the theoretical consumption calculated by using regression analysis of the historical data. The graph variance from the target focuses on the difference between real and expected (theoretical target) energy efficiency performance. The graph showing trends of specific energy ratios enables to benchmark the process with similar processes within or outside the company.
Obviously this is not an exhausting list of possibilities. Within M&T practice often graphs are used translating technical units into financial terms. Examples are pie or bar charts showing the energy cost breakdown, amount of achieved savings, cost trends etc.
Manager
Results of the data analysis were regularly discussed across all energy management levels and all responsible persons were encouraged to come up with ideas of possible energy saving options. This process was facilitated by the M&T project leader, all proposed ideas were reviewed from different aspects and feasible measures were implemented. The M&T system runs in a closed loop and checks results of already implemented measures periodically. The screen "Manager" provides a table for keeping all important information related to energy saving measures.
Continuation
There are displayed trends of cumulative savings for both selected energy cost centres on the last screen Continuing. While the Process cusum* trend oscillates around zero and from the annual point of view it is not transparent, any significant saving trend the Heating and domestic hot water cusum* proves outstanding level of savings starting with the heating season 2007-08.
*CUSUM refers here to calculation of cumulative sum of savings or losses against the original baseline (target) within given period of time.
CUSUM shows also change direction of a trend in savings/loses as visible from graphs within screen Continuation.